## BOQ_All_Jobs
Job | Bill | Category | Material | Work_Type | Item_No | Unit | Rate | BOQ_Qty | Qty_Used | Qty_Remaining | Pct_Used | BOQ_Cost | Actual_Cost | Cost_Difference | MOS_Qty | Claim1_Qty | Claim1_Amount | Claim2_Qty | Claim2_Amount | Claim3_Qty | Claim3_Amount | Claim4_Qty | Claim4_Amount | Rate_Only | Full_Description
EXT 81 Fase 1 | Preliminary and General Items | Camping site, stores, and toilets | Camping site, stores, and toilets | General | 1.1 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the erection of a site camp, the fencing thereof and the maintenance of the site
EXT 81 Fase 1 | Preliminary and General Items | Construction Machinery & Equipment | Construction Machinery & Equipment | General | 1.2 | Sum | 39900 | 1 | 0.6 | 0.4 | 60% | 39900 | 23940 | 15960 | 0 | 0.1 | 3990 | 0.3 | 11970 | 0.2 | 7980 | 0 | 0 | No | The total price for the supply, maintenance and removal of all construction machinery necessary
EXT 81 Fase 1 | Preliminary and General Items | Insurance of the works | Insurance of the works | General | 1.3 | Sum | 7000 | 1 | 1 | 0 | 100% | 7000 | 7000 | 0 | 0 | 0.1 | 700 | 0.3 | 2100 | 0.6 | 4200 | 0 | 0 | No | Total cost for the insurance of the works in accordance with the general conditions of contract which include free issue material to the value of
EXT 81 Fase 1 | Preliminary and General Items | Sureties | Sureties | General | 1.4 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the provision of the contract sureties -
EXT 81 Fase 1 | Preliminary and General Items | Contractors Supervision | Contractors Supervision | General | 1.5 | Sum | 76000 | 1 | 0.6 | 0.4 | 60% | 76000 | 45600 | 30400 | 0 | 0.1 | 7600 | 0.3 | 22800 | 0.2 | 15200 | 0 | 0 | No | The total price for supervisory site staff, the attendance of site meetings, inspections and
EXT 81 Fase 1 | Preliminary and General Items | Security | Security | General | 1.6 | Sum | 61750 | 1 | 0.45 | 0.55 | 45% | 61750 | 27787.5 | 33962.5 | 0 | 0 | 0 | 0.3 | 18525 | 0.15 | 9262.5 | 0 | 0 | No | Total cost for the provision of security at the contractor's site camp and on site where material and equipment
EXT 81 Fase 1 | Preliminary and General Items | Clearing of Site | Clearing of Site | General | 1.7 | Sum | 2375 | 1 | 0 | 1 | 0% | 2375 | 0 | 2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Allow for the clearing of site, the removal of scrap material and rubbish after the completion of the
EXT 81 Fase 1 | Preliminary and General Items | Safety Plan | Safety Plan – preparation | General | 1.8.1 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the preparation of a site specific safety plan that is in accordance with the Client's safety plan and OHS Act.
EXT 81 Fase 1 | Preliminary and General Items | Safety Plan | Safety Plan – compliance & safety gear | General | 1.8.2 | Sum | 5225 | 1 | 0.6 | 0.4 | 60% | 5225 | 3135 | 2090 | 0 | 0.1 | 522.5 | 0.25 | 1306.25 | 0.25 | 1306.25 | 0 | 0 | No | Total cost for the preparation of a site specific safety plan that is in accordance with the Client's safety plan and OHS Act. Total cost for the compliance to the safety plan for the duration of the contract which includes safety meetings, safety checks and checklist, safety representative,
EXT 81 Fase 1 | Preliminary and General Items | Provisional Allowances | Survey and Setting out | General | 1.9.1 | Sum | 10000 | 1 | 2.35 | -1.35 | 235% | 10000 | 23500 | -13500 | 0 | 0 | 0 | 1.5 | 15000 | 0.85 | 8500 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work to be carried out by a Registered
EXT 81 Fase 1 | Preliminary and General Items | Provisional Allowances | Profit & attendance | Percentage | 1.9.1 | Percentage | 23500 | 0.1 | 0.1 | 0 | 100% | 0 | 2350 | -2350 | 0 | 0 | 0 | 0.1 | 2350 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work to be carried out by a Registered
EXT 81 Fase 1 | Internal Electrical Infrastructure | Miniature substations | Miniature substations | Taking Delivery | 2.1.1 | No | 1500 | 1 | 0 | 1 | 0% | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | miniature substation complete including pre-cast concrete plinth. Mini-Sub to be Actom / JoCastro manufacture according to Rustenburg Local Municipality specification.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Miniature substations | Miniature substations | Supply (Plinth) | 2.1.2 | No | 7250 | 1 | 0 | 1 | 0% | 7250 | 0 | 7250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | miniature substation complete including pre-cast concrete plinth. Mini-Sub to be Actom / JoCastro manufacture according to Rustenburg Local Municipality specification.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Miniature substations | Miniature substations | Installation | 2.1.3 | No | 9131 | 1 | 0 | 1 | 0% | 9131 | 0 | 9131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | miniature substation complete including pre-cast concrete plinth. Mini-Sub to be Actom / JoCastro manufacture according to Rustenburg Local Municipality specification.
EXT 81 Fase 1 | Internal Electrical Infrastructure | B20 Ring Main Unit | B20 Ring Main Unit | Supply | 2.2.1 | No | 135423.75 | 1 | 0 | 1 | 0% | 135423.75 | 0 | 135423.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | mounted in a weatherproof canopy on a concrete plinth complete including heater and plinth plinth. Dimako Industries Interswitch Type B20 - Fuses 100A 3-Way with single fused T-off (Rate to include fuses).
EXT 81 Fase 1 | Internal Electrical Infrastructure | B20 Ring Main Unit | B20 Ring Main Unit | Installation | 2.2.2 | No | 5500 | 1 | 0 | 1 | 0% | 5500 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | mounted in a weatherproof canopy on a concrete plinth complete including heater and plinth plinth. Dimako Industries Interswitch Type B20 - Fuses 100A 3-Way with single fused T-off (Rate to include fuses).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cables | 400mm sq. 3C Al (WB) | Taking Delivery | 2.3.1 | m | 10 | 460 | 500 | -40 | 108.7% | 4600 | 5000 | -400 | 0 | 0 | 0 | 500 | 5000 | 0 | 0 | 0 | 0 | No | insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cables | 185mm sq. 3C Al | Taking Delivery | 2.3.2 | m | 10 | 20 | 20 | 0 | 100% | 200 | 200 | 0 | 0 | 0 | 0 | 20 | 200 | 0 | 0 | 0 | 0 | No | insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cables | 95mm sq. 3C Al | Taking Delivery | 2.3.3 | m | 10 | 800 | 800 | 0 | 100% | 8000 | 8000 | 0 | 0 | 0 | 0 | 800 | 8000 | 0 | 0 | 0 | 0 | No | insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cables | 400mm sq. 3C Al (WB) | Installation | 2.3.4 | m | 52 | 460 | 402 | 58 | 87.4% | 23920 | 20904 | 3016 | 0 | 0 | 0 | 402 | 20904 | 0 | 0 | 0 | 0 | No | insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cables | 185mm sq. 3C Al | Installation | 2.3.5 | m | 50 | 20 | 0 | 20 | 0% | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cables | 95mm sq. 3C Al | Installation | 2.3.6 | m | 45 | 800 | 300 | 500 | 37.5% | 36000 | 13500 | 22500 | 0 | 0 | 0 | 0 | 0 | 300 | 13500 | 0 | 0 | No | insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Terminations | 11kV Cable Terminations | Supply | 2.4.1 | No | 3607.25 | 5 | 0 | 5 | 0% | 18036.25 | 0 | 18036.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cable terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Cabac manufacture. 95mm sq. 3C Al
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Terminations | 11kV Cable Terminations | Installation | 2.4.2 | No | 6793.75 | 5 | 0 | 5 | 0% | 33968.75 | 0 | 33968.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cable terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Cabac manufacture. 95mm sq. 3C Al
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 400mm sq. 3C Al | Supply | 2.5.1 | No | 9911.25 | 1 | 0 | 1 | 0% | 9911.25 | 0 | 9911.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 400 - 185mm sq. 3C Al | Supply | 2.5.2 | No | 9911.25 | 2 | 0 | 2 | 0% | 19822.5 | 0 | 19822.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 185 - 95mm sq. 3C Al | Supply | 2.5.3 | No | 4507 | 2 | 0 | 2 | 0% | 9014 | 0 | 9014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 95mm sq. 3C Al | Supply | 2.5.4 | No | 4507 | 4 | 0 | 4 | 0% | 18028 | 0 | 18028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 400mm sq. 3C Al (WB) | Installation | 2.5.5 | No | 14364 | 1 | 0 | 1 | 0% | 14364 | 0 | 14364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 400 - 185mm sq. 3C Al | Installation | 2.5.6 | No | 14364 | 2 | 0 | 2 | 0% | 28728 | 0 | 28728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 185 - 95mm sq. 3C Al | Installation | 2.5.7 | No | 8960 | 2 | 0 | 2 | 0% | 17920 | 0 | 17920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | 11kV Cable Joints | 95mm sq. 3C Al | Installation | 2.5.8 | No | 8960 | 4 | 0 | 4 | 0% | 35840 | 0 | 35840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 4mm sq. 3C Cu | Supply | 2.6.1 | m | 53.65 | 50 | 0 | 50 | 0% | 2682.5 | 0 | 2682.5 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 2C Cu | Supply | 2.6.2 | m | 104.76 | 1150 | 1150 | 0 | 100% | 120474 | 120474 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 120474 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 25mm sq. 2C Cu | Supply | 2.6.3 | m | 163.2 | 270 | 0 | 270 | 0% | 44064 | 0 | 44064 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 150mm sq. 4C Solid Al | Supply | 2.6.4 | m | 335 | 280 | 270 | 10 | 96.4% | 93800 | 90450 | 3350 | 30 | 0 | 0 | 0 | 0 | 270 | 90450 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 185mm sq. 4C Solid Al | Supply | 2.6.5 | m | 391 | 400 | 270 | 130 | 67.5% | 156400 | 105570 | 50830 | 130 | 0 | 0 | 0 | 0 | 270 | 105570 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 4mm sq. 3C Cu | Installation | 2.6.6 | m | 8 | 50 | 0 | 50 | 0% | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 2C Cu | Installation | 2.6.7 | m | 15.5 | 1150 | 1150 | 0 | 100% | 17825 | 17825 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 17825 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 25mm sq. 2C Cu | Installation | 2.6.8 | m | 15.5 | 270 | 0 | 270 | 0% | 4185 | 0 | 4185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 150mm sq. 4C Solid Al | Installation | 2.6.9 | m | 37.5 | 280 | 270 | 10 | 96.4% | 10500 | 10125 | 375 | 0 | 0 | 0 | 0 | 0 | 270 | 10125 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cables | 185mm sq. 4C Solid Al | Installation | 2.6.10 | m | 37.5 | 400 | 270 | 130 | 67.5% | 15000 | 10125 | 4875 | 0 | 0 | 0 | 0 | 0 | 270 | 10125 | 0 | 0 | No | Bedded, SWA PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 4mm sq. 3C Cu | Supply | 2.1.1 | No | 45 | 2 | 0 | 2 | 0% | 90 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 2C Cu | Supply | 2.7.2 | No | 56 | 37 | 0 | 37 | 0% | 2072 | 0 | 2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 25mm sq. 2C Cu | Supply | 2.7.3 | No | 61.3 | 4 | 0 | 4 | 0% | 245.2 | 0 | 245.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 150mm sq. 4C Solid Al | Supply | 2.7.4 | No | 1808.7 | 6 | 0 | 6 | 0% | 10852.2 | 0 | 10852.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 185mm sq. 4C Solid Al | Supply | 2.7.5 | No | 1760 | 8 | 0 | 8 | 0% | 14080 | 0 | 14080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 4mm sq. 3C Cu | Installation | 2.7.6 | No | 48 | 2 | 0 | 2 | 0% | 96 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 2C Cu | Installation | 2.7.7 | No | 76 | 37 | 0 | 37 | 0% | 2812 | 0 | 2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 25mm sq. 2C Cu | Installation | 2.7.8 | No | 76 | 4 | 0 | 4 | 0% | 304 | 0 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 150mm sq. 4C Solid Al | Installation | 2.7.9 | No | 120 | 6 | 0 | 6 | 0% | 720 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 185mm sq. 4C Solid Al | Installation | 2.7.10 | No | 120 | 8 | 0 | 8 | 0% | 960 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Metal (Simmel) lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 16mm sq. 2C Cu | Supply | 2.8.1 | No | 24.38 | 37 | 0 | 37 | 0% | 902.06 | 0 | 902.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 25mm sq. 2C Cu | Supply | 2.8.2 | No | 42.12 | 4 | 0 | 4 | 0% | 168.48 | 0 | 168.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 95mm sq. 3C Al | Supply | 2.8.3 | No | 71.12 | 3 | 0 | 3 | 0% | 213.36 | 0 | 213.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 400mm sq. 3C Al | Supply | 2.8.4 | No | 128.75 | 2 | 2 | 0 | 100% | 257.5 | 257.5 | 0 | 0 | 0 | 0 | 2 | 257.5 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 16mm sq. 2C Cu | Installation | 2.8.5 | No | 16.8 | 37 | 0 | 37 | 0% | 621.6 | 0 | 621.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 25mm sq. 2C Cu | Installation | 2.8.6 | No | 16.8 | 4 | 0 | 4 | 0% | 67.2 | 0 | 67.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 95mm sq. 3C Al | Installation | 2.8.7 | No | 20 | 3 | 0 | 3 | 0% | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 400mm sq. 3C Al | Installation | 2.8.8 | No | 20 | 2 | 2 | 0 | 100% | 40 | 40 | 0 | 0 | 0 | 0 | 2 | 40 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 1 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 16mm sq. stranded BCEW | Supply | 2.9.1 | m | 41.8 | 550 | 445 | 105 | 80.9% | 22990 | 18601 | 4389 | 105 | 0 | 0 | 0 | 0 | 445 | 18601 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 50mm sq. stranded BCEW | Supply | 2.9.2 | m | 127.6 | 650 | 540 | 110 | 83.1% | 82940 | 68904 | 14036 | 110 | 0 | 0 | 0 | 0 | 540 | 68904 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 16mm sq. stranded BCEW | Installation | 2.9.3 | m | 7.5 | 550 | 445 | 105 | 80.9% | 4125 | 3337.5 | 787.5 | 0 | 0 | 0 | 0 | 0 | 445 | 3337.5 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 50mm sq. stranded BCEW | Installation | 2.9.4 | m | 10 | 650 | 540 | 110 | 83.1% | 6500 | 5400 | 1100 | 0 | 0 | 0 | 0 | 0 | 540 | 5400 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Earth Spikes | Earth Spikes | Supply | 2.10.1 | No | 300 | 12 | 0 | 12 | 0% | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cladded earth spikes complete including lug connections to BCEW and T-offs.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Earth Spikes | Earth Spikes | Installation | 2.10.2 | No | 130 | 12 | 0 | 12 | 0% | 1560 | 0 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cladded earth spikes complete including lug connections to BCEW and T-offs.
EXT 81 Fase 1 | Internal Electrical Infrastructure | Earthing of equipment | Mini-Sub earth | Supply | 2.9.1 | No | 2350 | 1 | 0 | 1 | 0% | 2350 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 81 Fase 1 | Internal Electrical Infrastructure | Earthing of equipment | B20 Earth | Supply | 2.9.2 | No | 2082 | 1 | 0 | 1 | 0% | 2082 | 0 | 2082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 81 Fase 1 | Internal Electrical Infrastructure | Earthing of equipment | Mini-Sub earth | Installation | 2.9.3 | No | 1570 | 1 | 0 | 1 | 0% | 1570 | 0 | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 81 Fase 1 | Internal Electrical Infrastructure | Earthing of equipment | B20 Earth | Installation | 2.9.4 | No | 1388 | 1 | 0 | 1 | 0% | 1388 | 0 | 1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 81 Fase 1 | Internal Electrical Infrastructure | Distribution Stubbies | 6 Way with 6 C/B's (RMS6) | Supply | 2.11.1 | No | 12022 | 3 | 0 | 3 | 0% | 36066 | 0 | 36066 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Distribution Stubbies | 9 Way with 9 C/B's (RMS9) | Supply | 2.11.2 | No | 14410 | 4 | 0 | 4 | 0% | 57640 | 0 | 57640 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Distribution Stubbies | 12 Way with 12 C/B's (RMS12) | Supply | 2.11.3 | No | 18000 | 1 | 0 | 1 | 0% | 18000 | 0 | 18000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Distribution Stubbies | 6 Way with 6 C/B's (RMS6) | Installation | 2.11.4 | No | 940 | 3 | 0 | 3 | 0% | 2820 | 0 | 2820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Distribution Stubbies | 9 Way with 9 C/B's (RMS9) | Installation | 2.11.5 | No | 940 | 4 | 0 | 4 | 0% | 3760 | 0 | 3760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Distribution Stubbies | 12 Way with 12 C/B's (RMS12) | Installation | 2.11.6 | No | 940 | 1 | 0 | 1 | 0% | 940 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 1 | Internal Electrical Infrastructure | Pressure Testing | VLF Pressure Test – New Cable/Line | General | 2.13.1 | No | 5780 | 1 | 0 | 1 | 0% | 5780 | 0 | 5780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the pressure testing of Medium voltage cables and other 11kV equipment prior to energizing. Pressure test to be in accordance with the SANS specification VLF Pressure Testing of 11kV 3 Core Cable prior to
EXT 81 Fase 1 | Internal Electrical Infrastructure | Pressure Testing | VLF Pressure Test – Existing Cable/Line | General | 2.13.2 | No | 5780 | 1 | 0 | 1 | 0% | 5780 | 0 | 5780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the pressure testing of Medium voltage cables and other 11kV equipment prior to energizing. Pressure test to be in accordance with the SANS specification VLF Pressure Testing of 11kV 3 Core Cable prior to VLF Pressure Testing of 11kV 3 Core Cable prior to
EXT 81 Fase 1 | Internal Electrical Infrastructure | Testing & Commissioning | Testing & Commissioning | General | 2.14 | Sum | 4500 | 1 | 0 | 1 | 0% | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the testing and commissioning of
EXT 81 Fase 1 | Streetlighting System | Low Voltage Cables | 4mm sq 4C Cu | Supply | 3.1.1 | m | 68 | 1200 | 700 | 500 | 58.3% | 81600 | 47600 | 34000 | 500 | 0 | 0 | 0 | 0 | 700 | 47600 | 0 | 0 | No | SWA PVC sheathed low voltage cables as specified
EXT 81 Fase 1 | Streetlighting System | Low Voltage Cables | 4mm sq 4C Cu | Installation | 3.1.2 | m | 8 | 1200 | 700 | 500 | 58.3% | 9600 | 5600 | 4000 | 0 | 0 | 0 | 0 | 0 | 700 | 5600 | 0 | 0 | No | SWA PVC sheathed low voltage cables as specified
EXT 81 Fase 1 | Streetlighting System | Bare Copper Earth Wire | 6mm sq stranded BCEW | Supply | 3.2.1 | m | 15.56 | 320 | 70 | 250 | 21.9% | 4979.2 | 1089.2 | 3890 | 250 | 0 | 0 | 0 | 0 | 70 | 1089.2 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 1 | Streetlighting System | Bare Copper Earth Wire | 6mm sq stranded BCEW | Installation | 3.2.2 | m | 7.5 | 320 | 70 | 250 | 21.9% | 2400 | 525 | 1875 | 0 | 0 | 0 | 0 | 0 | 70 | 525 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 1 | Streetlighting System | Low Voltage Cable Terminations | 4mm sq 4C Cu | Supply | 3.3.1 | No | 253 | 52 | 0 | 52 | 0% | 13156 | 0 | 13156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | termination of the following cables:
EXT 81 Fase 1 | Streetlighting System | Low Voltage Cable Terminations | 4mm sq 4C Cu | Installation | 3.3.2 | No | 105 | 52 | 0 | 52 | 0% | 5460 | 0 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | termination of the following cables:
EXT 81 Fase 1 | Streetlighting System | Streetlight poles | Streetlight poles | Supply | 3.4.1 | No | 5000 | 26 | 0 | 26 | 0% | 130000 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the supply and installation of the following streetlight poles complete including pole, pole top spiggot, base plate,excavation, backfilling and compaction of pole hole. Poles shall be of the Sectional Poles manufacture. Galvavized steel pole with 0.5m spiggot (Single) and anti-corrosion sleeve. (7m MH)
EXT 81 Fase 1 | Streetlighting System | Streetlight poles | Profit & attendance | Percentage | 3.4 | Percentage | 0 | 0.1 | 0.1 | 0 | 100% | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | No | Total price for the supply and installation of the following streetlight poles complete including pole, pole top spiggot, base plate,excavation, backfilling and compaction of pole hole. Poles shall be of the Sectional Poles manufacture. Galvavized steel pole with 0.5m spiggot (Single) and anti-corrosion sleeve. (7m MH)
EXT 81 Fase 1 | Streetlighting System | Streetlight poles | Streetlight poles | Installation | 3.4.2 | No | 450 | 26 | 0 | 26 | 0% | 11700 | 0 | 11700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the supply and installation of the following streetlight poles complete including pole, pole top spiggot, base plate,excavation, backfilling and compaction of pole hole. Poles shall be of the Sectional Poles manufacture. Galvavized steel pole with 0.5m spiggot (Single) and anti-corrosion sleeve. (7m MH)
EXT 81 Fase 1 | Streetlighting System | Streetlights | Streetlights | Supply | 3.5.1 | No | 2097 | 26 | 0 | 26 | 0% | 54522 | 0 | 54522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | streetlights complete including lamps, control gear etc Beka LEDLume Midi XP 88W Optic 5307
EXT 81 Fase 1 | Streetlighting System | Streetlights | Profit & attendance | Percentage | 3.5 | Percentage | 0 | 0.1 | 0.1 | 0 | 100% | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | 0.1 | 0 | No | streetlights complete including lamps, control gear etc Beka LEDLume Midi XP 88W Optic 5307
EXT 81 Fase 1 | Streetlighting System | Streetlights | Streetlights | Installation | 3.5.2 | No | 111 | 26 | 0 | 26 | 0% | 2886 | 0 | 2886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | streetlights complete including lamps, control gear etc Beka LEDLume Midi XP 88W Optic 5307
EXT 81 Fase 1 | Streetlighting System | Wiring of Streetlight poles | Wiring of Streetlight poles | Supply | 3.6.1 | No | 385 | 26 | 0 | 26 | 0% | 10010 | 0 | 10010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | stranded copper conductors for the wiring of the streetlight poles complete including earthwire and 5A CBI Type MCCB. (Total Rate per Pole) Galvavized steel pole with 0,5m spiggot 10m MH
EXT 81 Fase 1 | Streetlighting System | Wiring of Streetlight poles | Wiring of Streetlight poles | Installation | 3.6.2 | No | 165 | 26 | 0 | 26 | 0% | 4290 | 0 | 4290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | stranded copper conductors for the wiring of the streetlight poles complete including earthwire and 5A CBI Type MCCB. (Total Rate per Pole) Galvavized steel pole with 0,5m spiggot 10m MH
EXT 81 Fase 1 | General | Cable Marking Tape | Cable Marking Tape | Supply | 4.1.1 | m | 0.65 | 2150 | 955 | 1195 | 44.4% | 1397.5 | 620.75 | 776.75 | 0 | 0 | 0 | 402 | 261.3 | 553 | 359.45 | 0 | 0 | No | installed 300mm above cables in trenches
EXT 81 Fase 1 | General | Cable Marking Tape | Cable Marking Tape | Installation | 4.1.2 | m | 1 | 2150 | 955 | 1195 | 44.4% | 2150 | 955 | 1195 | 0 | 0 | 0 | 402 | 402 | 553 | 553 | 0 | 0 | No | installed 300mm above cables in trenches
EXT 81 Fase 1 | General | Concrete Cable Markers | Concrete Cable Markers | Supply | 4.2.1 | No | 150 | 5 | 2 | 3 | 40% | 750 | 300 | 450 | 0 | 0 | 0 | 2 | 300 | 0 | 0 | 0 | 0 | No | as specified.
EXT 81 Fase 1 | General | Concrete Cable Markers | Concrete Cable Markers | Installation | 4.2.2 | No | 65 | 5 | 2 | 3 | 40% | 325 | 130 | 195 | 0 | 0 | 0 | 2 | 130 | 0 | 0 | 0 | 0 | No | as specified.
EXT 81 Fase 1 | General | Concrete Cable Slabs | Concrete Cable Slabs | Supply | 4.3.1 | No | 65 | 20 | 0 | 20 | 0% | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | slabs directly above the cables - Slab size 1435 x 300 x 40mm (25MPa)
EXT 81 Fase 1 | General | Concrete Cable Slabs | Concrete Cable Slabs | Installation | 4.3.2 | No | 65 | 20 | 0 | 20 | 0% | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | slabs directly above the cables - Slab size 1435 x 300 x 40mm (25MPa)
EXT 81 Fase 1 | General | Sleeves for cables (Black) | 50mm dia | Supply | 4.4.1 | m | 20 | 20 | 0 | 20 | 0% | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 1 | General | Sleeves for cables (Black) | 110mm dia | Supply | 4.4.2 | m | 37 | 300 | 505 | -205 | 168.3% | 11100 | 18685 | -7585 | 0 | 350 | 12950 | 35 | 1295 | 120 | 4440 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 1 | General | Sleeves for cables (Black) | 160mm dia | Supply | 4.4.3 | m | 65 | 50 | 6 | 44 | 12% | 3250 | 390 | 2860 | 0 | 0 | 0 | 6 | 390 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 1 | General | Sleeves for cables (Black) | 50mm dia | Installation | 4.4.4 | m | 12.5 | 20 | 0 | 20 | 0% | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 1 | General | Sleeves for cables (Black) | 110mm dia | Installation | 4.4.5 | m | 15 | 300 | 505 | -205 | 168.3% | 4500 | 7575 | -3075 | 0 | 350 | 5250 | 35 | 525 | 120 | 1800 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 1 | General | Sleeves for cables (Black) | 160mm dia | Installation | 4.4.6 | m | 18 | 50 | 6 | 44 | 12% | 900 | 108 | 792 | 0 | 0 | 0 | 6 | 108 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 1 | General | Excavations | Soft Soil | General | 4.7.1 | cub.m | 145 | 900 | 317 | 583 | 35.2% | 130500 | 45965 | 84535 | 0 | 77 | 11165 | 240 | 34800 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 81 Fase 1 | General | Excavations | Soft Rock | General | 4.7.2 | cub.m | 145 | 250 | 124 | 126 | 49.6% | 36250 | 17980 | 18270 | 0 | 0 | 0 | 0 | 0 | 124 | 17980 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 81 Fase 1 | General | Excavations | Hard Rock | General | 4.7.3 | cub.m | 290 | 125 | 38 | 87 | 30.4% | 36250 | 11020 | 25230 | 0 | 38 | 11020 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 81 Fase 1 | General | Excavations | Soft Soil | General | 4.7.4 | cub.m | 315 | 100 | 26 | 74 | 26% | 31500 | 8190 | 23310 | 0 | 0 | 0 | 26 | 8190 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate Excavation of test pits for the purpose of locating existing services complete including backfilling thereafter
EXT 81 Fase 1 | General | Excavations | Backfilling | General | 4.7.5 | cub.m | 89 | 0 | 400 | -400 |  | 0 | 35600 | -35600 | 0 | 0 | 0 | 0 | 0 | 400 | 35600 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate Excavation of test pits for the purpose of locating existing services complete including backfilling thereafter
EXT 81 Fase 1 | General | Cable Bedding | Cable Bedding | Supply | 4.8.1 | cub.m | 192 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for cable bedding as specified.
EXT 81 Fase 1 | General | Cable Bedding | Cable Bedding | Installation | 4.8.2 | cub.m | 75.5 | 350 | 211 | 139 | 60.3% | 26425 | 15930.5 | 10494.5 | 0 | 0 | 0 | 81 | 6115.5 | 130 | 9815 | 0 | 0 | No | for cable bedding as specified.
EXT 81 Fase 1 | General | Horizontal Drilling of Sleeves | 160mm dia. sleeve | Supply | 4.9.1 | m | 959 | 15 | 24 | -9 | 160% | 14385 | 23016 | -8631 | 0 | 0 | 0 | 24 | 23016 | 0 | 0 | 0 | 0 | No | Horizontal drilling of sleeves for the purpose of a cable crossing across an existing tar road.
EXT 81 Fase 1 | General | Horizontal Drilling of Sleeves | 160mm dia. sleeve | Installation | 4.9.2 | m | 2194 | 15 | 20 | -5 | 133.3% | 32910 | 43880 | -10970 | 0 | 0 | 0 | 20 | 43880 | 0 | 0 | 0 | 0 | No | Horizontal drilling of sleeves for the purpose of a cable crossing across an existing tar road.
EXT 81 Fase 1 | General | Break and repairs to broken surfaces | Concrete slab - 100mm thick | General | 4.10.1 | sq. m | 540 | 10 | 0 | 10 | 0% | 5400 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the breaking and repairs of the following surfaces. Rate should include compaction of area to 90% MOD AASHTO priorto repairs.
EXT 81 Fase 1 | General | Break and repairs to broken surfaces | Paved Surface | General | 4.10.2 | sq. m | 540 | 20 | 0 | 20 | 0% | 10800 | 0 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the breaking and repairs of the following surfaces. Rate should include compaction of area to 90% MOD AASHTO priorto repairs.
EXT 81 Fase 2 | Preliminary and General Items | Camping site, stores, and toilets | Camping site, stores, and toilets | General | 1.1 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the erection of a site camp, the fencing thereof and the maintenance of the site
EXT 81 Fase 2 | Preliminary and General Items | Construction Machinery & Equipment | Construction Machinery & Equipment | General | 1.2 | Sum | 18750 | 1 | 0.5 | 0.5 | 50% | 18750 | 9375 | 9375 | 0 | 0.5 | 9375 | 0 | 0 | 0 | 0 | 0 | 0 | No | The total price for the supply, maintenance and removal of all construction machinery necessary
EXT 81 Fase 2 | Preliminary and General Items | Insurance of the works | Insurance of the works | General | 1.3 | Sum | 5000 | 1 | 1 | 0 | 100% | 5000 | 5000 | 0 | 0 | 1 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the insurance of the works in accordance with the general conditions of contract which include free issue material to the value of R660,000-00 up to
EXT 81 Fase 2 | Preliminary and General Items | Sureties | Sureties | General | 1.4 | Sum | 4287.5 | 1 | 1 | 0 | 100% | 4287.5 | 4287.5 | 0 | 0 | 1 | 4287.5 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the provision of the contract sureties -
EXT 81 Fase 2 | Preliminary and General Items | Contractors Supervision | Contractors Supervision | General | 1.5 | Sum | 40000 | 1 | 0.5 | 0.5 | 50% | 40000 | 20000 | 20000 | 0 | 0.5 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | No | The total price for supervisory site staff, the attendance of site meetings, inspections and
EXT 81 Fase 2 | Preliminary and General Items | Security | Security | General | 1.6 | Sum | 4100 | 1 | 1 | 0 | 100% | 4100 | 4100 | 0 | 0 | 1 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the provision of security at the contractor's site camp and on site where material and equipment have been
EXT 81 Fase 2 | Preliminary and General Items | Clearing of Site | Clearing of Site | General | 1.7 | Sum | 5250 | 1 | 0 | 1 | 0% | 5250 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Allow for the clearing of site, the removal of scrap material and rubbish after the completion of the
EXT 81 Fase 2 | Preliminary and General Items | Safety Plan | Safety Plan – preparation | General | 1.8.1 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the preparation of a site specific safety plan that is in accordance with the Client's safety plan and OHS Act.
EXT 81 Fase 2 | Preliminary and General Items | Safety Plan | Safety Plan – compliance & safety gear | General | 1.8.2 | Sum | 6300 | 1 | 0.5 | 0.5 | 50% | 6300 | 3150 | 3150 | 0 | 0.5 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the preparation of a site specific safety plan that is in accordance with the Client's safety plan and OHS Act. Total cost for the compliance to the safety plan for the duration of the contract which includes safety meetings, safety checks and checklist, safety representative,
EXT 81 Fase 2 | Preliminary and General Items | Provisional Allowances | Survey and Setting out | General | 1.9.1 | Sum | 10000 | 1 | 0.5 | 0.5 | 50% | 10000 | 5000 | 5000 | 0 | 0.5 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work
EXT 81 Fase 2 | Preliminary and General Items | Provisional Allowances | Profit & attendance | Percentage | 1.9.1 | Percentage | 10000 | 0.22 | 0.22 | 0 | 100% | 0 | 1100 | -1100 | 0 | 0.22 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cables | 70mm sq. 3C Al | Taking Delivery | 2.1.1 | m | 7.35 | 235 | 228 | 7 | 97% | 1727.25 | 1675.8 | 51.45 | 0 | 228 | 1675.8 | 0 | 0 | 0 | 0 | 0 | 0 | No | Taking deliovery and installation of the following 3C XLPE insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cables | 70mm sq. 3C Al | Installation | 2.1.2 | m | 31.5 | 235 | 228 | 7 | 97% | 7402.5 | 7182 | 220.5 | 0 | 228 | 7182 | 0 | 0 | 0 | 0 | 0 | 0 | No | Taking deliovery and installation of the following 3C XLPE insulated individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B).
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cable Terminations | Indoor | Supply | 2.2.1 | No | 2380.35 | 1 | 0 | 1 | 0% | 2380.35 | 0 | 2380.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cable Terminations | Outdoor | Supply | 2.2.2 | No | 3129 | 1 | 0 | 1 | 0% | 3129 | 0 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cable Terminations | Indoor | Installation | 2.2.3 | No | 3734.25 | 1 | 0 | 1 | 0% | 3734.25 | 0 | 3734.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cable Terminations | Outdoor | Installation | 2.2.4 | No | 4502.4 | 1 | 0 | 1 | 0% | 4502.4 | 0 | 4502.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cable Joints | 70mm sq. 3C Al | Supply | 2.3.1 | No | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Cable Joints | 70mm sq. 3C Al | Installation | 2.3.2 | No | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 2C Cu | Supply | 2.4.1 | m | 108 | 900 | 900 | 0 | 100% | 97200 | 97200 | 0 | 0 | 900 | 97200 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cables | 185mm sq. 4C Solid Al | Supply | 2.4.2 | m | 399 | 350 | 350 | 0 | 100% | 139650 | 139650 | 0 | 0 | 350 | 139650 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 2C Cu | Installation | 2.4.3 | m | 15.5 | 900 | 900 | 0 | 100% | 13950 | 13950 | 0 | 0 | 900 | 13950 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cables | 185mm sq. 4C Solid Al | Installation | 2.4.4 | m | 25 | 350 | 350 | 0 | 100% | 8750 | 8750 | 0 | 0 | 350 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 2C Cu | Supply | 2.5.1 | No | 110.5 | 24 | 0 | 24 | 0% | 2652 | 0 | 2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 185mm sq. 4C Solid Al | Supply | 2.5.2 | No | 714.5 | 8 | 0 | 8 | 0% | 5716 | 0 | 5716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 2C Cu | Installation | 2.5.3 | No | 96 | 24 | 0 | 24 | 0% | 2304 | 0 | 2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 2 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 185mm sq. 4C Solid Al | Installation | 2.5.4 | No | 235 | 8 | 0 | 8 | 0% | 1880 | 0 | 1880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 81 Fase 2 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 16mm sq. 2C Cu | Supply | 2.6.1 | No | 22.8 | 24 | 24 | 0 | 100% | 547.2 | 547.2 | 0 | 0 | 24 | 547.2 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 2 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 70mm sq. 3C Al | Supply | 2.6.2 | No | 66.4 | 1 | 1 | 0 | 100% | 66.4 | 66.4 | 0 | 0 | 1 | 66.4 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 2 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 16mm sq. 2C Cu | Installation | 2.6.3 | No | 16.8 | 24 | 24 | 0 | 100% | 403.2 | 403.2 | 0 | 0 | 24 | 403.2 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 2 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 70mm sq. 3C Al | Installation | 2.6.4 | No | 16.8 | 1 | 1 | 0 | 100% | 16.8 | 16.8 | 0 | 0 | 1 | 16.8 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 81 Fase 2 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 16mm sq. stranded BCEW | Supply | 2.7.1 | m | 38 | 150 | 294 | -144 | 196% | 5700 | 11172 | -5472 | 0 | 294 | 11172 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 2 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 50mm sq. stranded BCEW | Supply | 2.7.2 | m | 115.56 | 360 | 350 | 10 | 97.2% | 41601.6 | 40446 | 1155.6 | 0 | 350 | 40446 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 2 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 16mm sq. stranded BCEW | Installation | 2.7.3 | m | 6 | 150 | 294 | -144 | 196% | 900 | 1764 | -864 | 0 | 294 | 1764 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 2 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 50mm sq. stranded BCEW | Installation | 2.7.4 | m | 9 | 360 | 350 | 10 | 97.2% | 3240 | 3150 | 90 | 0 | 350 | 3150 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Terminal Structure | 11kV Terminal Structure | Supply | 2.8.1 | No | 9126 | 1 | 0 | 1 | 0% | 9126 | 0 | 9126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | structure complete including, 1300mm galv .cross arm, 11kV surge arresters, 100A drop out fuses and 3m 160mm dia kicker pipe on existing wooden T-off structure complete.
EXT 81 Fase 2 | Internal Electrical Infrastructure | 11kV Terminal Structure | 11kV Terminal Structure | Installation | 2.8.2 | No | 6260 | 1 | 0 | 1 | 0% | 6260 | 0 | 6260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | structure complete including, 1300mm galv .cross arm, 11kV surge arresters, 100A drop out fuses and 3m 160mm dia kicker pipe on existing wooden T-off structure complete.
EXT 81 Fase 2 | Internal Electrical Infrastructure | Earth Spikes | Earth Spikes | Supply | 2.9.1 | No | 225 | 5 | 0 | 5 | 0% | 1125 | 0 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cladded earth spikes complete including lug connections to BCEW and T-offs.
EXT 81 Fase 2 | Internal Electrical Infrastructure | Earth Spikes | Earth Spikes | Installation | 2.9.2 | No | 80 | 5 | 0 | 5 | 0% | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cladded earth spikes complete including lug connections to BCEW and T-offs.
EXT 81 Fase 2 | Internal Electrical Infrastructure | Distribution Stubbies | 12 Way with 12 C/B's (RMS12) | Taking Delivery | 2.10.1 | No | 350 | 4 | 0 | 4 | 0% | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 2 | Internal Electrical Infrastructure | Distribution Stubbies | 12 Way with 12 C/B's (RMS12) | Installation | 2.10.2 | No | 650 | 4 | 0 | 4 | 0% | 2600 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 81 Fase 2 | Internal Electrical Infrastructure | Pressure Testing | Pressure Testing | General | 2.11 | No | 2500 | 1 | 0 | 1 | 0% | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the pressure testing of Medium voltage cables and other 11kV equipment prior to energizing. Pressure test
EXT 81 Fase 2 | Internal Electrical Infrastructure | Testing & Commissioning | Testing & Commissioning | General | 2.12 | Sum | 2800 | 1 | 0 | 1 | 0% | 2800 | 0 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the testing and commissioning of
EXT 81 Fase 2 | General | Cable Marking Tape | Cable Marking Tape | Supply | 3.1.1 | m | 0.6 | 510 | 510 | 0 | 100% | 306 | 306 | 0 | 0 | 510 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | No | installed 300mm above cables in trenches
EXT 81 Fase 2 | General | Cable Marking Tape | Cable Marking Tape | Installation | 3.1.2 | m | 1 | 510 | 510 | 0 | 100% | 510 | 510 | 0 | 0 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | No | installed 300mm above cables in trenches
EXT 81 Fase 2 | General | Concrete Cable Markers | Concrete Cable Markers | Supply | 3.2.1 | No | 432 | 1 | 0 | 1 | 0% | 432 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | as specified.
EXT 81 Fase 2 | General | Concrete Cable Markers | Concrete Cable Markers | Installation | 3.2.2 | No | 65 | 1 | 0 | 1 | 0% | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | as specified.
EXT 81 Fase 2 | General | Concrete Cable Slabs | Concrete Cable Slabs | Supply | 3.3.1 | No | 450 | 5 | 0 | 5 | 0% | 2250 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | directly above the cables - Slab size 1435 x 300 x 40mm (25MPa)
EXT 81 Fase 2 | General | Concrete Cable Slabs | Concrete Cable Slabs | Installation | 3.3.2 | No | 120 | 5 | 0 | 5 | 0% | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | directly above the cables - Slab size 1435 x 300 x 40mm (25MPa)
EXT 81 Fase 2 | General | Sleeves for cables (Black) | 50mm dia | Supply | 3.4.1 | m | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 2 | General | Sleeves for cables (Black) | 110mm dia. Including steel draw wire | Supply | 3.4.2 | m | 36 | 300 | 125 | 175 | 41.7% | 10800 | 4500 | 6300 | 0 | 125 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 2 | General | Sleeves for cables (Black) | 160mm dia | Supply | 3.4.3 | m | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 2 | General | Sleeves for cables (Black) | 50mm dia | Installation | 3.4.4 | m | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 2 | General | Sleeves for cables (Black) | 110mm dia. including 4mm steel draw wire | Installation | 3.4.5 | m | 12.5 | 300 | 125 | 175 | 41.7% | 3750 | 1562.5 | 2187.5 | 0 | 125 | 1562.5 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 2 | General | Sleeves for cables (Black) | 160mm dia | Installation | 3.4.6 | m | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | sleeves for cables complete including draw wire and temporary end caps
EXT 81 Fase 2 | General | Sleeves for telephones | 12/10mm 7-way duct | Taking Delivery | 3.5.1 | m | 3 | 190 | 190 | 0 | 100% | 570 | 570 | 0 | 0 | 190 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | No | Micro duct sleeves for future telephone system.
EXT 81 Fase 2 | General | Sleeves for telephones | 12/10mm 2-way duct | Taking Delivery | 3.5.2 | m | 3 | 360 | 360 | 0 | 100% | 1080 | 1080 | 0 | 0 | 360 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | No | Micro duct sleeves for future telephone system.
EXT 81 Fase 2 | General | Sleeves for telephones | 12/10mm 7-way duct | Installation | 3.5.3 | m | 12 | 190 | 190 | 0 | 100% | 2280 | 2280 | 0 | 0 | 190 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | No | Micro duct sleeves for future telephone system.
EXT 81 Fase 2 | General | Sleeves for telephones | 12/10mm 2-way duct | Installation | 3.5.4 | m | 12 | 360 | 360 | 0 | 100% | 4320 | 4320 | 0 | 0 | 360 | 4320 | 0 | 0 | 0 | 0 | 0 | 0 | No | Micro duct sleeves for future telephone system.
EXT 81 Fase 2 | General | Telephone Manholes | Telephone Manholes | Taking Delivery | 3.6.1 | No | 150 | 4 | 0 | 4 | 0% | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Averge RHI Node 600 manhole - 40kN
EXT 81 Fase 2 | General | Telephone Manholes | Telephone Manholes | Installation | 3.6.2 | No | 450 | 4 | 0 | 4 | 0% | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Averge RHI Node 600 manhole - 40kN
EXT 81 Fase 2 | General | Endcaps for telephone sleeves | 2-way | Supply | 3.7.1 | No | 40 | 24 | 24 | 0 | 100% | 960 | 960 | 0 | 0 | 24 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 81 Fase 2 | General | Endcaps for telephone sleeves | 7-way | Supply | 3.7.2 | No | 67 | 8 | 8 | 0 | 100% | 536 | 536 | 0 | 0 | 8 | 536 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 81 Fase 2 | General | Endcaps for telephone sleeves | 2-way | Installation | 3.7.3 | No | 17 | 24 | 24 | 0 | 100% | 408 | 408 | 0 | 0 | 24 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 81 Fase 2 | General | Endcaps for telephone sleeves | 7-way | Installation | 3.7.4 | No | 22 | 8 | 8 | 0 | 100% | 176 | 176 | 0 | 0 | 8 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 81 Fase 2 | General | Excavations | Soft Soil | General | 3.8.1 | cub.m | 110 | 300 | 330 | -30 | 110% | 33000 | 36300 | -3300 | 0 | 330 | 36300 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 81 Fase 2 | General | Excavations | Soft Rock | General | 3.8.2 | cub.m | 110 | 90 | 0 | 90 | 0% | 9900 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 81 Fase 2 | General | Excavations | Hard Rock | General | 3.8.3 | cub.m | 252 | 45 | 3 | 42 | 6.7% | 11340 | 756 | 10584 | 0 | 3 | 756 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 81 Fase 2 | General | Excavations | Soft Soil | General | 3.8.4 | cub.m | 180 | 30 | 15 | 15 | 50% | 5400 | 2700 | 2700 | 0 | 15 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate Excavation of test pits for the purpose of locating existing services complete including backfilling thereafter
EXT 81 Fase 2 | General | Cable Bedding | Cable Bedding | Supply | 3.9.1 | cub.m | 192 | 70 | 73 | -3 | 104.3% | 13440 | 14016 | -576 | 0 | 73 | 14016 | 0 | 0 | 0 | 0 | 0 | 0 | No | for cable bedding as specified.
EXT 81 Fase 2 | General | Cable Bedding | Cable Bedding | Installation | 3.9.2 | cub.m | 75.5 | 70 | 73 | -3 | 104.3% | 5285 | 5511.5 | -226.5 | 0 | 73 | 5511.5 | 0 | 0 | 0 | 0 | 0 | 0 | No | for cable bedding as specified.
EXT 81 Fase 2 | General | Manhole drainage stone | Manhole drainage stone | Supply | 3.10.1 | cub.m | 900 | 0.5 | 0 | 0.5 | 0% | 450 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | of 10-15mm) below all manholes - 300x300mm (LxW) x 200mm think
EXT 81 Fase 2 | General | Manhole drainage stone | Manhole drainage stone | Installation | 3.10.2 | cub.m | 450 | 0.5 | 0 | 0.5 | 0% | 225 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | of 10-15mm) below all manholes - 300x300mm (LxW) x 200mm think
EXT 81 Fase 2 | General | Horizontal Drilling of Sleeves | 110mm dia. sleeve | Supply | 3.11.1 | m | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | Horizontal drilling of sleeves for the purpose of a cable crossing across an existing tar road.
EXT 81 Fase 2 | General | Horizontal Drilling of Sleeves | 110mm dia. sleeve | Installation | 3.11.2 | m | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes | Horizontal drilling of sleeves for the purpose of a cable crossing across an existing tar road.
EXT 81 Fase 2 | General | Repairs to broken surfaces | Concrete slab - 100mm thick | General | 3.12.1 | sq. m | 340 | 10 | 0 | 10 | 0% | 3400 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the repairs of the following surfaces. Rate should include compaction of area to 90% MOD AASHTO prior to repairs.
EXT 81 Fase 2 | General | Repairs to broken surfaces | Paved Surface | General | 3.12.2 | sq. m | 340 | 10 | 8 | 2 | 80% | 3400 | 2720 | 680 | 0 | 8 | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the repairs of the following surfaces. Rate should include compaction of area to 90% MOD AASHTO prior to repairs.
EXT 56 | Preliminary and General Items | Camping site, stores, and toilets | Camping site, stores, and toilets | General | 1.1 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the erection of a site camp, the fencing thereof and the maintenance of the site
EXT 56 | Preliminary and General Items | Construction Machinery & Equipment | Construction Machinery & Equipment | General | 1.2 | Sum | 42000 | 1 | 0.55 | 0.45 | 55% | 42000 | 23100 | 18900 | 0 | 0.33 | 13860 | 0.22 | 9240 | 0 | 0 | 0 | 0 | No | The total price for the supply, maintenance and removal of all construction machinery necessary
EXT 56 | Preliminary and General Items | Insurance of the works | Insurance of the works | General | 1.3 | Sum | 8000 | 1 | 0.55 | 0.45 | 55% | 8000 | 4400 | 3600 | 0 | 0.33 | 2640 | 0.22 | 1760 | 0 | 0 | 0 | 0 | No | Total cost for the insurance of the works in accordance with the general conditions of contract which include free issue material to the value of R1,360,000-00
EXT 56 | Preliminary and General Items | Sureties | Sureties | General | 1.4 | Sum | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the provision of the contract sureties -
EXT 56 | Preliminary and General Items | Contractors Supervision | Contractors Supervision | General | 1.5 | Sum | 80000 | 1 | 0.55 | 0.45 | 55% | 80000 | 44000 | 36000 | 0 | 0.33 | 26400 | 0.22 | 17600 | 0 | 0 | 0 | 0 | No | The total price for supervisory site staff, the attendance of site meetings, inspections and
EXT 56 | Preliminary and General Items | Security | Security | General | 1.6 | Sum | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the provision of security at the contractor's site camp and on site where material and equipment have been
EXT 56 | Preliminary and General Items | Clearing of Site | Clearing of Site | General | 1.7 | Sum | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Allow for the clearing of site, the removal of scrap material and rubbish after the completion of the
EXT 56 | Preliminary and General Items | Safety Plan | Safety Plan – preparation | General | 1.8.1 | Sum | 0 | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the preparation of a site specific safety plan that is in accordance with the Client's safety plan and OHS Act.
EXT 56 | Preliminary and General Items | Safety Plan | Safety Plan – compliance & safety gear | General | 1.8.2 | Sum | 5500 | 1 | 0.55 | 0.45 | 55% | 5500 | 3025 | 2475 | 0 | 0.33 | 1815 | 0 | 0 | 0.22 | 1210 | 0 | 0 | No | Total cost for the preparation of a site specific safety plan that is in accordance with the Client's safety plan and OHS Act. Total cost for the compliance to the safety plan for the duration of the contract which includes safety meetings, safety checks and checklist, safety representative,
EXT 56 | Preliminary and General Items | Provisional Allowances | Survey and Setting out | General | 1.9.1 | Sum | 10000 | 1 | 0 | 1 | 0% | 10000 | 0 | 10000 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work
EXT 56 | Preliminary and General Items | Provisional Allowances | Profit & attendance | Percentage | 1.9.1 | % | 0 | 0.1 | 0.1 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work
EXT 56 | Preliminary and General Items | Provisional Allowances | Provisional Material | General | 1.9.2 | Sum | 20000 | 1 | 0 | 1 | 0% | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work Material Total Cost for the supply of any material possibly not
EXT 56 | Preliminary and General Items | Provisional Allowances | Profit & attendance | Percentage | 1.9.2 | % | 0 | 0.1 | 0.1 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Survey and Setting out Total Cost for the calculation and survey of all boundary and servitude positions as well as joint and cable position. Work Material Total Cost for the supply of any material possibly not
EXT 56 | Internal Electrical Infrastructure | Miniature substations | Miniature substations | Taking Delivery | 2.1.1 | No | 1500 | 1 | 0 | 1 | 0% | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | miniature substation complete including pre-cast concrete plinth. Minisub will be Actom / JC Jocastro manufacture according to Rustenburg Local Municipality specification.Contractor to allow for stogare, safekeeping and transport to site when required.
EXT 56 | Internal Electrical Infrastructure | Miniature substations | Miniature substations | Supply (Plinth) | 2.1.2 | No | 7250 | 1 | 0 | 1 | 0% | 7250 | 0 | 7250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | miniature substation complete including pre-cast concrete plinth. Minisub will be Actom / JC Jocastro manufacture according to Rustenburg Local Municipality specification.Contractor to allow for stogare, safekeeping and transport to site when required.
EXT 56 | Internal Electrical Infrastructure | Miniature substations | Miniature substations | Installation | 2.1.3 | No | 9131 | 1 | 0 | 1 | 0% | 9131 | 0 | 9131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | miniature substation complete including pre-cast concrete plinth. Minisub will be Actom / JC Jocastro manufacture according to Rustenburg Local Municipality specification.Contractor to allow for stogare, safekeeping and transport to site when required.
EXT 56 | Internal Electrical Infrastructure | B20 Ring Main Unit | B20 Ring Main Unit | Supply | 2.2.1 | No | 135423.75 | 1 | 0 | 1 | 0% | 135423.75 | 0 | 135423.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | mounted in a weatherproof canopy on a concrete plinth complete including heater. Dimako Industries Interswitch Type B20 - Fuses 100A 3-Way with single fused T-off (Rate to include fuses).
EXT 56 | Internal Electrical Infrastructure | B20 Ring Main Unit | B20 Ring Main Unit | Installation | 2.2.2 | No | 5500 | 1 | 0 | 1 | 0% | 5500 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | mounted in a weatherproof canopy on a concrete plinth complete including heater. Dimako Industries Interswitch Type B20 - Fuses 100A 3-Way with single fused T-off (Rate to include fuses).
EXT 56 | Internal Electrical Infrastructure | 11kV Cables | 400mm sq. 3C Al (WB) | Taking Delivery | 2.3.1 | m | 10 | 540 | 300 | 240 | 55.6% | 5400 | 3000 | 2400 | 0 | 0 | 0 | 300 | 3000 | 0 | 0 | 0 | 0 | No | individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B). Contractor to allow for storage, safekeeping and transport to site when required
EXT 56 | Internal Electrical Infrastructure | 11kV Cables | 70mm sq. 3C Al | Taking Delivery | 2.3.2 | m | 10 | 200 | 200 | 0 | 100% | 2000 | 2000 | 0 | 0 | 0 | 0 | 200 | 2000 | 0 | 0 | 0 | 0 | No | individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B). Contractor to allow for storage, safekeeping and transport to site when required
EXT 56 | Internal Electrical Infrastructure | 11kV Cables | 400mm sq. 3C Al (WB) | Installation | 2.3.3 | m | 52 | 540 | 280 | 260 | 51.9% | 28080 | 14560 | 13520 | 0 | 0 | 0 | 280 | 14560 | 0 | 0 | 0 | 0 | No | individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B). Contractor to allow for storage, safekeeping and transport to site when required
EXT 56 | Internal Electrical Infrastructure | 11kV Cables | 70mm sq. 3C Al | Installation | 2.3.4 | m | 45 | 200 | 150 | 50 | 75% | 9000 | 6750 | 2250 | 0 | 0 | 0 | 150 | 6750 | 0 | 0 | 0 | 0 | No | individually copper tape screened, unarmoured, PVC sheathed Cu / Al cables (Type B). Contractor to allow for storage, safekeeping and transport to site when required
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Terminations | 400mm sq. 3C Al (WB) | Supply | 2.4.1 | No | 5902.25 | 2 | 0 | 2 | 0% | 11804.5 | 0 | 11804.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem manufacture
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Terminations | 70mm sq. 3C Al | Supply | 2.4.2 | No | 3607.25 | 3 | 0 | 3 | 0% | 10821.75 | 0 | 10821.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem manufacture
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Terminations | 400mm sq. 3C Al (WB) | Installation | 2.4.3 | No | 7291.25 | 2 | 0 | 2 | 0% | 14582.5 | 0 | 14582.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem manufacture
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Terminations | 70mm sq. 3C Al | Installation | 2.4.4 | No | 6793.75 | 3 | 0 | 3 | 0% | 20381.25 | 0 | 20381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | terminations complete including lugs. Work to be carried out by a Specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Termination shall be of type 3M, Tank or Raychem manufacture
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Joints | 400mm sq. 3C Al | Supply | 2.5.1 | No | 9911.25 | 3 | 0 | 3 | 0% | 29733.75 | 0 | 29733.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Joints | 70mm sq. 3C Al | Supply | 2.5.2 | No | 4507 | 1 | 0 | 1 | 0% | 4507 | 0 | 4507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Joints | 400mm sq. 3C Al (WB) | Installation | 2.5.3 | No | 14364 | 3 | 0 | 3 | 0% | 43092 | 0 | 43092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 56 | Internal Electrical Infrastructure | 11kV Cable Joints | 70mm sq. 3C Al | Installation | 2.5.4 | No | 8960 | 1 | 0 | 1 | 0% | 8960 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | complete including ferrules. Work to be carried out by a specialist company (Uni-Test or Cabac). Should another company be proposed, approval is to be obtained from the Engineer. Joints shall be of type 3M, Tank or Raychem. Cost should include cable spiking/tracing cost if required by Contractor
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 4mm sq. 3C Cu | Supply | 2.6.1 | m | 53.65 | 130 | 130 | 0 | 100% | 6974.5 | 6974.5 | 0 | 0 | 0 | 0 | 130 | 6974.5 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 4C Cu | Supply | 2.6.2 | m | 194.46 | 50 | 40 | 10 | 80% | 9723 | 7778.4 | 1944.6 | 10 | 40 | 7778.4 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 2C Cu | Supply | 2.6.3 | m | 104.76 | 1200 | 240 | 960 | 20% | 125712 | 25142.4 | 100569.6 | 960 | 240 | 25142.4 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 25mm sq. 2C Cu | Supply | 2.6.4 | m | 163.2 | 120 | 0 | 120 | 0% | 19584 | 0 | 19584 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 150mm sq. 4C Solid Al | Supply | 2.6.5 | m | 335 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 185mm sq. 4C Solid Al | Supply | 2.6.6 | m | 391 | 1000 | 475 | 525 | 47.5% | 391000 | 185725 | 205275 | 525 | 475 | 185725 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 4mm sq. 3C Cu | Installation | 2.6.7 | m | 8 | 130 | 130 | 0 | 100% | 1040 | 1040 | 0 | 0 | 0 | 0 | 130 | 1040 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 4C Cu | Installation | 2.6.8 | m | 15.5 | 50 | 40 | 10 | 80% | 775 | 620 | 155 | 0 | 40 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 16mm sq. 2C Cu | Installation | 2.6.9 | m | 15.5 | 1150 | 240 | 910 | 20.9% | 17825 | 3720 | 14105 | 0 | 240 | 3720 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 25mm sq. 2C Cu | Installation | 2.6.10 | m | 15.5 | 110 | 0 | 110 | 0% | 1705 | 0 | 1705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 150mm sq. 4C Solid Al | Installation | 2.6.11 | m | 37.5 | 1 | 0 | 1 | 0% | 37.5 | 0 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cables | 185mm sq. 4C Solid Al | Installation | 2.6.12 | m | 37.5 | 1000 | 475 | 525 | 47.5% | 37500 | 17812.5 | 19687.5 | 0 | 475 | 17812.5 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified (SANS 1507)
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 4mm sq. 3C Cu | Supply | 2.7.1 | No | 45 | 2 | 0 | 2 | 0% | 90 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 4C Cu | Supply | 2.7.2 | No | 82.84 | 1 | 0 | 1 | 0% | 82.84 | 0 | 82.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 2C Cu | Supply | 2.7.3 | No | 56 | 38 | 0 | 38 | 0% | 2128 | 0 | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 25mm sq. 2C Cu | Supply | 2.7.4 | No | 61.3 | 2 | 0 | 2 | 0% | 122.6 | 0 | 122.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 150mm sq. 4C Solid Al | Supply | 2.7.5 | No | 1808.7 | 1 | 0 | 1 | 0% | 1808.7 | 0 | 1808.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 185mm sq. 4C Solid Al | Supply | 2.7.6 | No | 1760 | 28 | 0 | 28 | 0% | 49280 | 0 | 49280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 4mm sq. 3C Cu | Installation | 2.7.7 | No | 48 | 2 | 0 | 2 | 0% | 96 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 4C Cu | Installation | 2.7.8 | No | 76 | 1 | 0 | 1 | 0% | 76 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 16mm sq. 2C Cu | Installation | 2.7.9 | No | 76 | 38 | 0 | 38 | 0% | 2888 | 0 | 2888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 25mm sq. 2C Cu | Installation | 2.7.10 | No | 76 | 2 | 0 | 2 | 0% | 152 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 150mm sq. 4C Solid Al | Installation | 2.7.11 | No | 120 | 1 | 0 | 1 | 0% | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Low Voltage Cable Terminations | 185mm sq. 4C Solid Al | Installation | 2.7.12 | No | 120 | 28 | 0 | 28 | 0% | 3360 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | lugs for Al cable, k-clamps for feeder and service cables for the termination of the following cables:
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 16mm sq. 2C Cu | Supply | 2.8.1 | No | 24.38 | 38 | 18 | 20 | 47.4% | 926.44 | 438.84 | 487.6 | 0 | 18 | 438.84 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 25mm sq. 2C Cu | Supply | 2.8.2 | No | 42.12 | 2 | 0 | 2 | 0% | 84.24 | 0 | 84.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 70mm sq. 3C Al | Supply | 2.8.3 | No | 71.12 | 2 | 2 | 0 | 100% | 142.24 | 142.24 | 0 | 0 | 0 | 0 | 2 | 142.24 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 400mm sq. 3C Al | Supply | 2.8.4 | No | 128.75 | 2 | 2 | 0 | 100% | 257.5 | 257.5 | 0 | 0 | 0 | 0 | 2 | 257.5 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 16mm sq. 2C Cu | Installation | 2.8.5 | No | 16.8 | 38 | 18 | 20 | 47.4% | 638.4 | 302.4 | 336 | 0 | 18 | 302.4 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 25mm sq. 2C Cu | Installation | 2.8.6 | No | 16.8 | 2 | 0 | 2 | 0% | 33.6 | 0 | 33.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 70mm sq. 3C Al | Installation | 2.8.7 | No | 20 | 2 | 2 | 0 | 100% | 40 | 40 | 0 | 0 | 0 | 0 | 2 | 40 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Heat Shrinkable End Caps | 400mm sq. 3C Al | Installation | 2.8.8 | No | 20 | 2 | 2 | 0 | 100% | 40 | 40 | 0 | 0 | 0 | 0 | 2 | 40 | 0 | 0 | 0 | 0 | No | for the following cables
EXT 56 | Internal Electrical Infrastructure | Earthing of equipment | Mini-Sub earth | Supply | 2.9.1 | No | 2350 | 1 | 0 | 1 | 0% | 2350 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 56 | Internal Electrical Infrastructure | Earthing of equipment | B20 Earth | Supply | 2.9.2 | No | 2082 | 1 | 0 | 1 | 0% | 2082 | 0 | 2082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 56 | Internal Electrical Infrastructure | Earthing of equipment | Mini-Sub earth | Installation | 2.9.3 | No | 1570 | 1 | 0 | 1 | 0% | 1570 | 0 | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 56 | Internal Electrical Infrastructure | Earthing of equipment | B20 Earth | Installation | 2.9.4 | No | 1388 | 1 | 0 | 1 | 0% | 1388 | 0 | 1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | comprising 50mm sq. bare copper earth wire a minimum of 4 x 1.5m x 16mm dia. Copper claded earth spikes with brazed T-Off's & terminations. Earth to be installed below precast plint with links to equipment earth bar
EXT 56 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 16mm sq. stranded BCEW | Supply | 2.10.1 | m | 41.8 | 550 | 120 | 430 | 21.8% | 22990 | 5016 | 17974 | 430 | 120 | 5016 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 56 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 50mm sq. stranded BCEW | Supply | 2.10.2 | m | 127.6 | 700 | 305 | 395 | 43.6% | 89320 | 38918 | 50402 | 395 | 305 | 38918 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 56 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 16mm sq. stranded BCEW | Installation | 2.10.3 | m | 7.5 | 550 | 120 | 430 | 21.8% | 4125 | 900 | 3225 | 0 | 120 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 56 | Internal Electrical Infrastructure | Bare Copper Earth Wire | 50mm sq. stranded BCEW | Installation | 2.10.4 | m | 10 | 700 | 305 | 395 | 43.6% | 7000 | 3050 | 3950 | 0 | 305 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | No | including brazed T-Off's & terminations.
EXT 56 | Internal Electrical Infrastructure | Earth Spikes | Earth Spikes | Supply | 2.11.1 | No | 300 | 3 | 0 | 3 | 0% | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cladded earth spikes complete including lug connections to BCEW and T-offs.
EXT 56 | Internal Electrical Infrastructure | Earth Spikes | Earth Spikes | Installation | 2.11.2 | No | 130 | 3 | 0 | 3 | 0% | 390 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | cladded earth spikes complete including lug connections to BCEW and T-offs.
EXT 56 | Internal Electrical Infrastructure | Distribution Stubbies | 6 Way with 6 C/B's | Supply | 2.12.1 | No | 12022 | 4 | 0 | 4 | 0% | 48088 | 0 | 48088 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 56 | Internal Electrical Infrastructure | Distribution Stubbies | 9 Way with 9 C/B's | Supply | 2.12.2 | No | 14410 | 1 | 0 | 1 | 0% | 14410 | 0 | 14410 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 56 | Internal Electrical Infrastructure | Distribution Stubbies | 12 Way with 12 C/B's | Supply | 2.12.3 | No | 18000 | 9 | 0 | 9 | 0% | 162000 | 0 | 162000 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 56 | Internal Electrical Infrastructure | Distribution Stubbies | 6 Way with 6 C/B's | Installation | 2.12.4 | No | 940 | 4 | 0 | 4 | 0% | 3760 | 0 | 3760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 56 | Internal Electrical Infrastructure | Distribution Stubbies | 9 Way with 9 C/B's | Installation | 2.12.5 | No | 940 | 1 | 0 | 1 | 0% | 940 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 56 | Internal Electrical Infrastructure | Distribution Stubbies | 12 Way with 12 C/B's | Installation | 2.12.6 | No | 940 | 9 | 0 | 9 | 0% | 8460 | 0 | 8460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Distribution Stubby, complete with base frame, circuit breakers and internal wiring in accordance with RLM requirements. (3CR12 Powder Coated Avocado Green)
EXT 56 | Internal Electrical Infrastructure | Pressure Testing | VLF Pressure Test – New Cable/Line | General | 2.13.1 | No | 5780 | 2 | 0 | 2 | 0% | 11560 | 0 | 11560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the pressure testing of Medium voltage cables and other 11kV equipment prior to energizing. Pressure test to be in accordance with the SANS specification VLF Pressure Testing of 11kV 3 Core Cable prior to
EXT 56 | Internal Electrical Infrastructure | Pressure Testing | VLF Pressure Test – Existing Cable/Line | General | 2.13.2 | No | 5780 | 2 | 0 | 2 | 0% | 11560 | 0 | 11560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the pressure testing of Medium voltage cables and other 11kV equipment prior to energizing. Pressure test to be in accordance with the SANS specification VLF Pressure Testing of 11kV 3 Core Cable prior to VLF Pressure Testing of 11kV 3 Core Cable prior to
EXT 56 | Internal Electrical Infrastructure | Testing & Commissioning | Testing & Commissioning | General | 2.14 | Sum | 4500 | 1 | 0 | 1 | 0% | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total cost for the testing and commissioning of
EXT 56 | Internal Electrical Infrastructure | Additional Items Required to complete the project | Joints | General | 2.15.1 | No | 3054.11 | 1 | 0 | 1 | 0% | 3054.11 | 0 | 3054.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No
EXT 56 | Streetlighting System | Low Voltage Cables | 6mm sq 2C Cu | Supply | 3.1.1 | m | 56.65 | 950 | 340 | 610 | 35.8% | 53817.5 | 19261 | 34556.5 | 610 | 340 | 19261 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified
EXT 56 | Streetlighting System | Low Voltage Cables | 6mm sq 2C Cu | Installation | 3.1.2 | m | 6.8 | 950 | 340 | 610 | 35.8% | 6460 | 2312 | 4148 | 0 | 340 | 2312 | 0 | 0 | 0 | 0 | 0 | 0 | No | PVC sheathed low voltage cables as specified
EXT 56 | Streetlighting System | Bare Copper Earth Wire | 6mm sq stranded BCEW | Supply | 3.2.1 | m | 15.56 | 200 | 160 | 40 | 80% | 3112 | 2489.6 | 622.4 | 40 | 30 | 466.8 | 130 | 2022.8 | 0 | 0 | 0 | 0 | No | brazed T-Off's & terminations.
EXT 56 | Streetlighting System | Bare Copper Earth Wire | 6mm sq stranded BCEW | Installation | 3.2.2 | m | 7.5 | 200 | 160 | 40 | 80% | 1500 | 1200 | 300 | 0 | 30 | 225 | 130 | 975 | 0 | 0 | 0 | 0 | No | brazed T-Off's & terminations.
EXT 56 | Streetlighting System | Low Voltage Cable Terminations | 6mm sq 2C Cu | Supply | 3.3.1 | No | 253 | 44 | 0 | 44 | 0% | 11132 | 0 | 11132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | termination of the following cables:
EXT 56 | Streetlighting System | Low Voltage Cable Terminations | 6mm sq 2C Cu | Installation | 3.3.2 | No | 105 | 44 | 0 | 44 | 0% | 4620 | 0 | 4620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | termination of the following cables:
EXT 56 | Streetlighting System | Streetlight poles | Streetlight poles | Supply | 3.4.1 | No | 3250 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the supply and installation of the following streetlight poles complete including pole, pole top spigot, base plate, excavation, backfilling and compaction of pole hole. Poles shall be of the Sectional Poles manufacture. Galvanized steel pole with 0.5m spigot (Single) and anti- corrosion sleeve. (5m MH)
EXT 56 | Streetlighting System | Streetlight poles | Streetlight poles | Installation | 3.4.2 | No | 450 | 22 | 0 | 22 | 0% | 9900 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Total price for the supply and installation of the following streetlight poles complete including pole, pole top spigot, base plate, excavation, backfilling and compaction of pole hole. Poles shall be of the Sectional Poles manufacture. Galvanized steel pole with 0.5m spigot (Single) and anti- corrosion sleeve. (5m MH)
EXT 56 | Streetlighting System | Streetlights | Streetlights | Taking Delivery | 3.5.1 | No | 55 | 22 | 0 | 22 | 0% | 1210 | 0 | 1210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | streetlights complete including lamps, control gear etc Beka LEDLume 29W Solar
EXT 56 | Streetlighting System | Streetlights | Streetlights | Installation | 3.5.2 | No | 111 | 22 | 0 | 22 | 0% | 2442 | 0 | 2442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | streetlights complete including lamps, control gear etc Beka LEDLume 29W Solar
EXT 56 | Streetlighting System | Wiring of Streetlight poles | Wiring of Streetlight poles | Supply | 3.6.1 | No | 541 | 22 | 0 | 22 | 0% | 11902 | 0 | 11902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | stranded copper conductors for the wiring of the streetlight poles complete including earthwire and 5A CBI Type MCCB as well as Eurolux C014 12V 30W Power Supply (Total Rate per Pole)
EXT 56 | Streetlighting System | Wiring of Streetlight poles | Wiring of Streetlight poles | Installation | 3.6.2 | No | 115 | 22 | 0 | 22 | 0% | 2530 | 0 | 2530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | stranded copper conductors for the wiring of the streetlight poles complete including earthwire and 5A CBI Type MCCB as well as Eurolux C014 12V 30W Power Supply (Total Rate per Pole)
EXT 56 | General | Cable Marking Tape | Cable Marking Tape | Supply | 4.1.1 | m | 0.65 | 1850 | 605 | 1245 | 32.7% | 1202.5 | 393.25 | 809.25 | 0 | 305 | 198.25 | 300 | 195 | 0 | 0 | 0 | 0 | No | installed 300mm above cables in trenches
EXT 56 | General | Cable Marking Tape | Cable Marking Tape | Installation | 4.1.2 | m | 1 | 1850 | 605 | 1245 | 32.7% | 1850 | 605 | 1245 | 0 | 305 | 305 | 300 | 300 | 0 | 0 | 0 | 0 | No | installed 300mm above cables in trenches
EXT 56 | General | Concrete Cable Markers | Concrete Cable Markers | Supply | 4.2.1 | No | 150 | 5 | 0 | 5 | 0% | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | as specified.
EXT 56 | General | Concrete Cable Markers | Concrete Cable Markers | Installation | 4.2.2 | No | 65 | 5 | 0 | 5 | 0% | 325 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | as specified.
EXT 56 | General | Concrete Cable Slabs | Concrete Cable Slabs | Supply | 4.3.1 | No | 65 | 20 | 0 | 20 | 0% | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | directly above the cables - Slab size 1435 x 300 x 40mm (25MPa)
EXT 56 | General | Concrete Cable Slabs | Concrete Cable Slabs | Installation | 4.3.2 | No | 65 | 20 | 0 | 20 | 0% | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | directly above the cables - Slab size 1435 x 300 x 40mm (25MPa)
EXT 56 | General | Sleeves for cables (Black) | 50mm dia | Supply | 4.4.1 | m | 20 | 10 | 0 | 10 | 0% | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 56 | General | Sleeves for cables (Black) | 110mm dia | Supply | 4.4.2 | m | 37 | 400 | 182 | 218 | 45.5% | 14800 | 6734 | 8066 | 0 | 50 | 1850 | 132 | 4884 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 56 | General | Sleeves for cables (Black) | 160mm dia | Supply | 4.4.3 | m | 65 | 50 | 0 | 50 | 0% | 3250 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 56 | General | Sleeves for cables (Black) | 50mm dia | Installation | 4.4.4 | m | 12.5 | 10 | 0 | 10 | 0% | 125 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 56 | General | Sleeves for cables (Black) | 110mm dia | Installation | 4.4.5 | m | 15 | 400 | 182 | 218 | 45.5% | 6000 | 2730 | 3270 | 0 | 50 | 750 | 132 | 1980 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 56 | General | Sleeves for cables (Black) | 160mm dia | Installation | 4.4.6 | m | 18 | 50 | 0 | 50 | 0% | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for cables complete including draw wire and temporary end caps
EXT 56 | General | Excavations | Soft Soil | General | 4.5.1 | cub.m | 145 | 600 | 280 | 320 | 46.7% | 87000 | 40600 | 46400 | 0 | 100 | 14500 | 180 | 26100 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 56 | General | Excavations | Soft Rock | General | 4.5.2 | cub.m | 145 | 160 | 0 | 160 | 0% | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 56 | General | Excavations | Hard Rock | General | 4.5.3 | cub.m | 290 | 80 | 0 | 80 | 0% | 23200 | 0 | 23200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 56 | General | Excavations | Soft Soil | General | 4.5.4 | cub.m | 315 | 30 | 20 | 10 | 66.7% | 9450 | 6300 | 3150 | 0 | 1.5 | 472.5 | 0 | 0 | 18.5 | 5827.5 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate Excavation of test pits for the purpose of locating existing services complete including backfilling thereafter
EXT 56 | General | Cable Bedding | Cable Bedding | Supply | 4.6.1 | cub.m | 0 | 120 | 0 | 120 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | for cable bedding as specified.
EXT 56 | General | Cable Bedding | Cable Bedding | Installation | 4.6.2 | cub.m | 75.5 | 120 | 50 | 70 | 41.7% | 9060 | 3775 | 5285 | 0 | 0 | 0 | 0 | 0 | 50 | 3775 | 0 | 0 | No | for cable bedding as specified.
EXT 56 | General | Horizontal Drilling of Sleeves | 160mm dia. sleeve | Supply | 4.7.1 | m | 959 | 10 | 0 | 10 | 0% | 9590 | 0 | 9590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Horizontal drilling of sleeves for the purpose of a cable crossing across an existing tar road.
EXT 56 | General | Horizontal Drilling of Sleeves | 160mm dia. sleeve | Installation | 4.7.2 | m | 2194 | 10 | 0 | 10 | 0% | 21940 | 0 | 21940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Horizontal drilling of sleeves for the purpose of a cable crossing across an existing tar road.
EXT 56 | Fibre Manholes and Sleeves | Sleeves for telephones | 50mm dia | Supply | 5.1.1 | m | 20 | 450 | 0 | 450 | 0% | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for Fiber System complete including drawwire
EXT 56 | Fibre Manholes and Sleeves | Sleeves for telephones | 110mm dia | Supply | 5.1.2 | m | 37 | 800 | 0 | 800 | 0% | 29600 | 0 | 29600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for Fiber System complete including drawwire
EXT 56 | Fibre Manholes and Sleeves | Sleeves for telephones | 50mm dia | Installation | 5.1.3 | m | 12.5 | 450 | 400 | 50 | 88.9% | 5625 | 5000 | 625 | 0 | 400 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for Fiber System complete including drawwire
EXT 56 | Fibre Manholes and Sleeves | Sleeves for telephones | 110mm dia | Installation | 5.1.4 | m | 15 | 800 | 0 | 800 | 0% | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | sleeves for Fiber System complete including drawwire
EXT 56 | Fibre Manholes and Sleeves | Telephone Manholes | Telephone Manholes | Supply | 5.2.1 | No | 2415 | 20 | 0 | 20 | 0% | 48300 | 0 | 48300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | precast concrete manholes. Manholes should be suitable for installation in the road / parkings and rate should include the cover
EXT 56 | Fibre Manholes and Sleeves | Telephone Manholes | Telephone Manholes | Installation | 5.2.2 | No | 550 | 20 | 0 | 20 | 0% | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | precast concrete manholes. Manholes should be suitable for installation in the road / parkings and rate should include the cover
EXT 56 | Fibre Manholes and Sleeves | Endcaps for telephone sleeves | 50mm dia | Supply | 5.3.1 | No | 22 | 42 | 0 | 42 | 0% | 924 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 56 | Fibre Manholes and Sleeves | Endcaps for telephone sleeves | 110mm dia | Supply | 5.3.2 | No | 31.5 | 50 | 0 | 50 | 0% | 1575 | 0 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 56 | Fibre Manholes and Sleeves | Endcaps for telephone sleeves | 50mm dia | Installation | 5.3.3 | No | 15 | 42 | 0 | 42 | 0% | 630 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 56 | Fibre Manholes and Sleeves | Endcaps for telephone sleeves | 110mm dia | Installation | 5.3.4 | No | 22 | 50 | 0 | 50 | 0% | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | fibre sleeves sleeves as listed above
EXT 56 | Fibre Manholes and Sleeves | Excavations | Soft Soil | General | 5.4.1 | cub.m | 145 | 420 | 0 | 420 | 0% | 60900 | 0 | 60900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 56 | Fibre Manholes and Sleeves | Excavations | Soft Rock | General | 5.4.2 | cub.m | 145 | 120 | 0 | 120 | 0% | 17400 | 0 | 17400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate
EXT 56 | Fibre Manholes and Sleeves | Excavations | Hard Rock | General | 5.4.3 | cub.m | 290 | 60 | 0 | 60 | 0% | 17400 | 0 | 17400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Excavation, backfilling, import of suitable backfilling where necessary, consolidation, compaction and making good of trenches in the following soil conditions. Disposal of material unsuitable for backfilling included in rate